## 4 Month
# | Phases | Activities | M1 |  |  |  | M2 |  |  |  | M3 |  |  |  |  | M4
|  |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17
1 | Project Kick Off | Resources Alignment | bar: M1 W1
2 | Solution Discussion | Solution Workshops (Integration Details) | bar: M1 W1 to M1 W2
3 | Solution Development | Hardware Procurement | bar: M1 W1 to M1 W4
4 |  | Setup & Installing of Hardware | bar: M2 W5 to M3 W10
5 |  | Development, Workflow Configuration Setup | bar: M1 W3 to M3 W10
6 |  | Testing & Remediation | bar: M3 W9 to M3 W10
7 |  | Solution Sign-off from Cient | bar: M3 W10
8 | Solution Testing & Rollout | SIT & SIT Remediation | bar: M3 W10 to M3 W11
9 |  | Key User Training | bar: M3 W12
10 |  | UAT & UAT Remediation | bar: M3 W13
11 |  | UAT Sign-off | bar: M3 W13
12 | Solution Deployment & Support | DEV to PROD Cutover | bar: M4 W14
13 |  | Go-Live | bar: M4 W14
14 |  | Hypercare & Support | bar: M4 W14 to M4 W17