## 6 months (P 0,1,2) + Hyper (3) (hidden)
# | Phases |  | Activities | M1 |  |  |  | M2 |  |  |  | M3 |  |  |  |  | M4 |  |  |  | M5 |  |  |  | M6 |  |  |  |  | M7-M12
|  |  |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26
1 | Logistics & Mobilization | Project Kick Off | Logistics & Mobilization of Resources | bar: M1 W1 to M1 W4
2 |  |  | Project Plan | bar: M1 W2
3 |  | Solution Discussion | Solution Workshops | bar: M1 W2 to M1 W3
4 |  |  | Requirement gathering for Dashboard, Alerts & Integration | bar: M1 W2 to M1 W3
5 |  |  | Pilot Site identified | bar: M1 W3
6 |  |  | Requirement Sign-off | bar: M1 W4
7 |  |  | Revised Project Plan | bar: M1 W4
8 |  |  | Revised Project Plan Sign-off | bar: M1 W4
9 | Pregate, CISF Gate In, NSFT Gate In, NSFT Gate Out, Survey Gate Out, CISF Gate Out, Load/Unload Point by RTGCs, ITT Gate In, ITT Gate Out, Rake Check In, Load/Unload Point by RMGCs, Rake Check Out | Solution Design, Setup & Develop | Hardware Procurement | bar: M1 W1 to M2 W8
10 |  |  | Setup & Installing of Hardware | bar: M2 W5 to M3 W13
11 |  |  | API Developments & Configuration | bar: M1 W3 to M4 W17
12 |  |  | Login Creations for Key Users | bar: M2 W6 to M4 W17
13 |  |  | Unit Testing Pilot Site (Stage wise) | bar: M2 W7 to M3 W11
14 |  |  | Remediation of Pilot Site (Stage wise) | bar: M3 W10 to M3 W11
15 |  |  | Development & Rollout of Checklist | bar: M3 W10 to M3 W13
16 |  |  | Unit Testing & Remediation | bar: M3 W12 to M4 W17
17 |  |  | Development & Setup Sign-off | bar: M3 W12 to M4 W17
18 |  | Solution Testing | SIT | bar: M5 W18 to M5 W21
19 |  |  | SIT Remediation | bar: M5 W20 to M5 W21
20 |  |  | Key User Training | bar: M6 W22 to M6 W23
21 |  |  | UAT | bar: M6 W24
22 |  |  | UAT Remediation | bar: M6 W25
23 |  |  | Testing Sign-off | bar: M6 W25
24 |  | Solution Deployment & Support | DEV to PROD Cutover | bar: M6 W26
25 |  |  | Go-Live | bar: M6 W26
26 |  |  | Hypercare & Support | bar: M6 W26

## 6 months (P 0,1,2) + Hyper
# | Phases | Activities | M1 |  |  |  | M2
|  |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8
1 | Project Kick Off | Resources Alignment with ABG Trading | bar: M1 W1
2 | Solution Discussion | Solution Workshops (SAP Integration Details) | bar: M1 W1
3 | Solution Development | API Developments & Configuration | bar: M1 W1 to M1 W2
4 |  | Unit Testing | bar: M1 W2
5 |  | Development Sign-off | bar: M1 W2
6 | Solution Testing | SIT & SIT Remediation | bar: M1 W3
8 |  | Key User Training | bar: M1 W3
9 |  | UAT & UAT Remediation | bar: M1 W4
11 |  | Testing Sign-off | bar: M1 W4
12 | Solution Deployment & Support | DEV to PROD Cutover | bar: M1 W4
13 |  | Go-Live | bar: M1 W4
14 |  | Hypercare & Support | bar: M2 W5 to M2 W8

## 6 months (P 0,1,2) + Hyper (2) (hidden)
# | Phases |  | Activities | M1 |  |  |  | M2 |  |  |  | M3 |  |  |  |  | M4 |  |  |  | M5 |  |  |  | M6 |  |  |  |  | M7
|  |  |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30
1 | Phase 0 | Project Kick Off | Logistics & Mobilization of Resources | bar: M1 W1 to M1 W4
2 |  |  | Project Plan | bar: M1 W2
3 |  | Solution Discussion | Solution Workshops | bar: M1 W2 to M1 W3
4 |  |  | Requirement gathering for Dashboard, Alerts & Integration | bar: M1 W2 to M1 W3
5 |  |  | Pilot Site identified | bar: M1 W3
6 |  |  | Requirement Sign-off | bar: M1 W4
7 |  |  | Revised Project Plan | bar: M1 W4
8 |  |  | Revised Project Plan Sign-off | bar: M1 W4
9 | Phase 1 | Solution Design, Setup & Develop | Hardware Procurement | bar: M1 W1 to M2 W8
10 |  |  | Setup & Installing of Hardware | bar: M2 W5 to M3 W12
11 |  |  | API Developments & Configuration | bar: M1 W3 to M5 W20
12 |  |  | Login Creations for Key Users | bar: M2 W6 to M5 W20
13 |  |  | Unit Testing Pilot Site (Stage wise) | bar: M2 W7 to M3 W11
14 |  |  | Remediation of Pilot Site (Stage wise) | bar: M3 W10 to M3 W11
15 |  |  | Development & Rollout of Checklist | bar: M3 W10 to M3 W13
16 |  |  | Unit Testing & Remediation | bar: M3 W12 to M3 W13
17 |  |  | Development & Setup Sign-off | bar: M3 W12 to M3 W13
18 |  | Solution Testing | SIT | bar: M4 W14 to M4 W16
19 |  |  | SIT Remediation | bar: M4 W17
20 |  |  | Key User Training | bar: M5 W18
21 |  |  | UAT | bar: M5 W19
22 |  |  | UAT Remediation | bar: M5 W20
23 |  |  | Testing Sign-off | bar: M5 W20
24 |  | Solution Deployment & Support | DEV to PROD Cutover | bar: M5 W21
25 |  |  | Go-Live | bar: M5 W21
26 |  |  | Hypercare & Support | bar: M5 W21 to M7 W30
27 | Phase 2 | Solution Design, Setup & Develop | Setup & Installing of Hardware | bar: M4 W14 to M5 W21
28 |  |  | Unit Testing & Remediation | bar: M4 W17 to M5 W21
29 |  | Solution Testing | SIT | bar: M6 W22 to M6 W23
30 |  |  | SIT Remediation | bar: M6 W23
31 |  |  | Key User Training | bar: M6 W24
32 |  |  | UAT | bar: M6 W25
33 |  |  | UAT Remediation | bar: M6 W25
34 |  |  | Testing Sign-off | bar: M6 W25
35 |  | Solution Deployment & Support | DEV to PROD Cutover | bar: M6 W26
36 |  |  | Go-Live | bar: M6 W26
37 |  |  | Hypercare & Support | bar: M6 W26 to M7 W30